Green Belt Project Report

(Your Name Here)

Improved access to standard knee high compression stockings.

Submitted:

Executive Summary

Problem Statement:

Standard knee-high compression stocking orders averaged 6-8 weeks for the Veteran to obtain at a wide variation in pricing ($24.06-$90.77 per pair).

Business Case:

At the inception of this project, we had no established Veteran Hospital (VA) staff trained to fit the 320 standard knee high (8-15mmhg, 20-30mmhg and 30-40mmhg) out of 360 plus annual requests for Veterans to obtain a form of compression stockings. Compression stockings are issued for a variety of conditions to help improve venous blood flow and decrease edema in the extremities. Such conditions could include post-surgical, lymphedema, venous ulcers, venous disease and general edema for example. There was no established staffing, clinic, standard operating procedures (SOP) or standardization of any kind to support issuance of standard knee high compression stockings at the VA. As a result service was provided at a higher cost per pair with lengthy delays of up to 6-8 weeks with 46% of orders not being filled.

Performance Levels:

- Time from consults issued to closure of purchase order pre requested. (long waits)

- Not using of national contract items. (Cost)

- Not using VA clinical staff to fit Veterans to stockings.

Root Cause:

A lack of inventory to issue from combined with a lack of trained staff to measure and train Veterans to allow for in house issuance of standard knee high stockings was noted. As a result, this lead to a reliance on outside vendors to order stockings through. This required the stocking vendor in a timely manner to complete all the scheduling, measuring, issuing and then billing the VA.

Improvement Options:

- Identify clinical staff already available at VA whose scope of practice allows for the training and measuring of compression stockings.

- Develop training programs to competency VA clinical staff.

- Utilize VA National contract compression stockings as working inventory.

- Establish process to place consult and record measurements and trainings.

Control Plan:

- Train clinical supervisors to train new hires and re-competency staff.

- Created PAR levels for all stock items

- Created new process for recording information.

- Train all staff in new process

Conclusions, Recommendations and Business Results:

Remove Text Box and Fill in.

Define

To begin our process, a team was identified:

- Process Owners –Chief of Hospital Education Sadi O (Training Phase), Chief of Primary Care- Dr. Mickey Mouse (Order Phase), & Chief of Prosthetics Dr. Michael Urban (Issuance Phase)

- Champion – Associate Chief of Staff Dr. Tyler Seguin

- Black Belt Coach- Dr. Michael Urban

- Green Belt Candidate-	Your Name

- The working team included: primary care, CBOC, and specialty care clinic supervisors; Betty Bop Supervisory Prosthetic Representative.

The initial problem was identified by Betty Bop, Dr. Michael Urban, Primary Care providers and the voice of the Veterans.

Initial Problem Statement: “Standard knee high compression stockings orders for Veteran take a long time to obtain (6-8wks) at a wide variation in pricing from outside vendors.”

Refined Problem Statement:  Standard knee high compression stockings orders averaged 6-8 weeks for the Veteran to obtain at a wide variation in pricing ($24.06-$90.77 per pair).

Goals

- Reduce wait times for Veterans to obtain standard knee stockings from 6-8 wks. to same day by 5/30/18.

- Reduce number of standard knee high stockings order requested not fulfilled by 25% by 5/30/18.

- Reduce price variations by $70 per pair for standard knee high stockings by 5/30/18.

In order to determine what the actual problem was, we identified our measures as;

- The cost per pair of stockings

- Days from consult placed to when closed.

- Number of consults not fulfilled.

We also identified our customers as:

- Clinicians who want timely issuance of standard knee high stockings.

- Veterans who want timely issuance of standard knee high stockings.

And our suppliers are:

- Primary, Specialty, and CBOC clinics at VA

| VA Stocking SIPOC |  |  |  |  |
| --- | --- | --- | --- | --- |
| Suppliers | Inputs | Process | Outputs | Customers |
| Primary Care Clinics Specialty Care Clinics CBOC Clinics | Consults for Std. Knee High Compression Stockings Stockings | See process map under Measure | Issuance of Std. Knee High Compression Stockings to Veterans. Incomplete Consult/order Purchase order reconciliations for each order. | Veterans Clinical Providers |

The process shows a high ratio on non-value added steps (red and yellow) in the process increasing potential risk for waste and delays to Veteran care.

Measure

The team’s next step was to determine what data needed to be collected and how we would accomplish the task.  All dates of when a consult was submitted and closed are recorded in the Veteran’s prosthetic suspense and prosthetic record (2319) which includes vendor name, number of pairs issued, and total price. This information is able to be extracted at any time for comparable time ranges based upon each purchase order or stock issue of standard knee high stockings. Your Name  would be responsible for obtaining this data and analyzing this for a 2 month period of time pre (1/15/15-2/28/15) and post (1/1/17-2/28/17) implantation of any changes. The data was validate with consistency noted between each rater for pre-data collection process change noted as noted in pre msa-xbar (see msa-xbar chart pre data below for cost and item received). The data method was used to monitor progress toward the project’s goals. The current process sigma capability demonstrates between 32%-52% of orders are never filled which further supports the voice of the customer which initiated the systematic review of the stocking ordering and issuance process (see pre-data defects tables below). The histogram located in the appendix (pages 16 and 18) shows the average days and price per pair yielded wide variation. This is supported by the xbar and r chart for pre-process data located in appendix (pages 17-18) demonstrates a wide variation and an unstable process in the number of days and price per pair for each order. The upper and lower control limits (UCL/LCU) may need to be lowered to improve the process mean.

| Attribute MSA Analysis Received |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Number and Type Mistake By Operator |  |  |  |  |  |  |  |
|  |  | OP 1 | OP 2 | OP 3 | Total |  |  |
| Truth | A | 0 | 0 | 0 | 0 | <-reject falsely |  |
|  | R | 0 | 0 | 0 | 0 | <-accept falsely |  |
| Inspection Capability |  |  |  |  |  |  |  |
|  |  | OP 1 | OP 2 | OP 3 | Total |  |  |
| Effectiveness |  | 1 | 1 | 1 | 1 |  |  |
| P(FR) |  | 0 | 0 | 0 | 0 |  |  |
| P(FA) |  | 0 | 0 | 0 | 0 |  |  |
| Bias |  | NA | NA | NA | NA |  |  |

Remove Text Box and Fill in.

Pre-Data Incomplete Orders (Defects):

| Product Summary Report |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Total |  |  |  | Sigma |
| Characteristic | Defects | Units | Opportunities | Opportunities | DPU | DPO | DPMO | Capability |
| Pre | 80 | 175 | 1 | 175 | 0.45714 | 0.45714 | 457142.857 | 1.6076 |
| Total | 80 |  | 0 | 175 |  | 0.45714 | 457142.857 | 1.6076 |

Remove Text Box and Fill in.

Pre-Data Incomplete Orders Per VA Vendor Utilized (Defects):

| Product Summary Report |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Total |  |  |  | Sigma |
| Characteristic | Defects | Units | Opportunities | Opportunities | DPU | DPO | DPMO | Capability |
| ACME | 48 | 93 | 1 | 93 | 0.51613 | 0.51613 | 516129.032 | Exceeds Bounds |
| Heads & Tails | 11 | 25 | 1 | 25 | 0.44000 | 0.44000 | 440000.000 | 1.6510 |
| SOCKS USA | 9 | 28 | 1 | 28 | 0.32143 | 0.32143 | 321428.571 | 1.9637 |
| My | 12 | 29 | 1 | 29 | 0.41379 | 0.41379 | 413793.103 | 1.7178 |
| Total | 80 |  | 0 | 175 |  | 0.45714 | 457142.857 | 1.6076 |

Remove Text Box and Fill in.

- Tools Used:    MSA, Histogram, DPM, Sigma Capabiltiy, Summary of Stats , SIPOC Chart, Value Stream Map

Analyize

Once all our data was collected and Sigma Zone tools used, we developed our Cause and Effect diagram as noted below. The primary root cause we first focused on was people which allowed us to identify clinical providers already within in the VA to complete measuring and education which is required. From here we were then able to incorporate the other primary root causes of technology, environment, process, materials and equipment into the process re-design. We also created the new process map to determine value added vs non-value added steps.  The contributing factors to poor issuance of standard knee high stockings and pricing were identified through brainstorming and use of an affinity diagram. Orders were reviewed from fiscal year (FY) 15 and FY 17 date ranges of Januaray 1st  to February 28th. Data was pulled from the Veterans prosthetics suspense consult record and prosthetics 2319 record. Data measured was date of consult placed by the provider to date consult closed by purchase order indicating order completed or by NR code indicating order was not completed. Price per order was recorded and the number of pairs per order along with vendor who was providing service to the Veteran.

Pre-Data:

| Pre Days Summary |  | Pre Price per Pair |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Count | 175 | Count | 95 |  |  |
| Mean | 48.65142857 | Mean | 71.47894737 |  |  |
| Median | 21 | Median | 66.5 |  |  |
| Mode | 0 | Mode | 48.125 |  |  |
| Max | 726 | Max | 375 |  |  |
| Min | 0 | Min | 19.6875 |  |  |
| Range | 726 | Range | 355.3125 |  |  |
| Std Dev (Pop) | 102.2093017 | Std Dev (Pop) | 54.26956849 |  |  |
| Std Dev (Sample) | 102.5025858 | Std Dev (Sample) | 54.55747273 |  |  |
| Variance (Pop) | 10446.74136 | Variance (Pop) | 2945.186064 |  |  |
| Variance (Sample) | 10506.7801 | Variance (Sample) | 2976.517831 |  |  |
| 95% Conf. Interval for Mean |  | 95% Conf. Interval for Mean |  |  |  |
| Upper Limit | 63.94451189 | Upper Limit | 82.59287234 |  |  |
| Lower Limit | 33.35834525 | Lower Limit | 60.3650224 |  |  |
| 99% Conf. Interval for Mean |  | 99% Conf. Interval for Mean |  |  |  |
| Upper Limit | 68.83137723 | Upper Limit | 86.195545 |  |  |
| Lower Limit | 28.47147991 | Lower Limit | 56.76234974 |  |  |

Remove Text Box and Fill in.

Remove Text Box and Fill in.

1-Way ANOVA

Remove Text Box and Fill in.

Remove Text Box and Fill in.

- Tools Used:     Cause and Effect Diagram, XbarR, Histogram, Summary Stats, CpK Analysis, DPM, Sigma Capability

Improve:

To improve the pre-data process, pre-data was assessed and a cost-benefit analysis was completed with stakeholders to assess available resources and costs associated with each option. The question was how to obtain fitters for VA in order to measure and size Veterans per order to allow for issuance of inventory of the national contract items. The identified options from the cause and effect diagram were compared to an impact effort matrix to prioritize the best option to pursue (see below C&E/Impact table and impact effort matrix).  To higher certified fitters for this sole purpose (High effort and High Impact) which would require increase costs in the means of salaries, benefits, space, support staff for scheduling of visits and equipment to support the position (exam tables, computers etc.). The other option considered was to utilize current VA staff (High Impact, Low Effort) where measuring, sizing, and training in the donning of the stockings were already available and would need competency training. This option from a cost-benefit analysis demonstrated that better utilization of resources was in the use of clinical licensed practical nurses and registered nurses who were already seeing the Veterans in clinic. The process was redesigned with no cost for training to competency the initial staff who would be completing the measuring.

C&E/Impact Table

| High Impact, Low Effort | Cause and Effect Diagram |
| --- | --- |
| Clinical VA Staff to Fit Stockings | Reduce dependence on multiple vendors |
|  | Reduce delays with 5 days to process |
|  | Lack of space for additional staff/fitters |
|  | Reduce Vendors do not report/update VA |
|  | Lack of fitters on site |
| Creating Inventory at VA | Lack of inventory/none on site |

Impact Effort Matrix

Remove Text Box and Fill in.

Post Stocking Process Design:

| # of Steps | Pre- Process | Post Process |
| --- | --- | --- |
| Value Added | 3 | 3 |
| Non-Value (NV) but Necessary | 7 | 4 |
| Non-Value (NV) Added | 3 | 2 |
| % Reduction in NV steps |  | 60% |

Remove Text Box and Fill in.

Post-Data:

Remove Text Box and Fill in.

Post-Data Incomplete Orders (Defects):

Remove Text Box and Fill in.

1-Way ANOVA

| ANOVA Analysis |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Source of Variation | SS | df | MS | F | P-value |
| Between Groups | 209040.4 | 1 | 209040.364 | 50.86133 | 3.99E-12 |
| Within Groups | 1845393 | 449 | 4110.00558 |  |  |
| Total | 2054433 | 450 |  |  |  |
| Group Summary |  |  |  |  |  |
| Group | Count | Average | Std Dev |  |  |
| Number of Days to Complete (PRE) | 175 | 48.651429 | 102.502586 |  |  |
| Number of Days to Complete (POST) | 276 | 4.4710145 | 7.91150327 |  |  |

Remove Text Box and Fill in.

Control

The final results of this project include the following competency check list (see appendix titled: Compression Stocking Competency Check) nursing and hospital education are utilizing to train and re-train on an annual basis all staff in how to measure for standard knee high stockings.

Pre- cost mean was (Fill In) per order of 4 pairs of stockings per order x (Fill In) completed stockings orders equals over 2 months $ (Fill In)  1-year approximate average cost for issuance equaling $ (Fill In)  estimated cost per year ($ (Fill In) x (Fill In) = $ (Fill In) ). Post cost mean price was $ (Fill In)  per 4 pairs of stockings per order x (Fill In)  completed stockings orders equals over 2 months $ (Fill In)  in average cost with a 1-year approximate average cost for issuance equaling $ (Fill In)  estimated cost per year ($ (Fill In) x (Fill In) = $ (Fill In)  ).

Post process change savings equals an estimated $(Fill In) ($ (Fill In) pre-process cost - $ (Fill In) post-process cost = (Fill In)  ) in savings with an increase issuance by (Fill In) ( (Fill In) completed post-process orders – (Fill In) completed pre-process orders = (Fill In) orders) post-process standard knee-high stockings issued.

Average number of days pre-process equaled (Fill In) with post-process issuance average days decreased to (Fill In) days for completed orders. Post process there still were (Fill In) orders or (Fill In) not completed due to clinical staff not measuring the Veteran to allow for issuance.

Lessons learned from the process redesign yielded (Fill In with you recommendations and perceived challenges with what you have read above).

RACI Chart

| Task/Person (POC)-Department | Hospital Education | Chief of Primary Care (clinical) | \RN- Staff | Chief of Prosthetics- price/processing | Prosthetics Staff |
| --- | --- | --- | --- | --- | --- |
| Clinical Staff Re-Competency | C | A | R | I | - |
| Initial Staff Training | C | R | R | I | - |
| Checking Consults for Issuance Measures/Size | - | I | I | A | R |
| Entering Consults | - | R | A | I | I |
| Measuring and Sizing of Veteran (Enter onto Consult) | - | A | R | I | I |

| Code | Stands for | This is the person who is…. |
| --- | --- | --- |
| R | Responsible | Responsible for performing the task or creating the document |
| A | Accountable | Accountable for the task or document such as the project manager, supervisor , or technical lead |
| C | Consult | Provides consulting or expertise to the person responsible for the task or document and others. |
| I | Inform | Informed of task progress or results, usually by the person responsible. |

Appendix:

Pre- Data number of Days:

The histogram shows (Fill In 1 sentence) .

XBar and R Chart for pre-process data demonstrates (Fill In)

Pre- Data Cost per Order of Stockings:

The histogram shows (Fill In 1 sentence) .

XBar and R Chart for pre-process data demonstrates (Fill In)

Post- Data number of Days:

The histogram shows (Fill In 1 sentence) .

XBar and R Chart for pre-process data demonstrates (Fill In)

Post- Data Cost per Order of Stockings:

The histogram shows (Fill In 1 sentence) .

XBar and R Chart for pre-process data demonstrates (Fill In)

Stocking Compentency Training Signoff Used by Clinical Staff

| Compression Stocking Competency Check | Date: |  |  |
| --- | --- | --- | --- |
| Employee and phone ext.: |  |  |
| Supervisor: |  |  |
| Service Location: |  |  |
|  | X = Completed |  | Table A |  |  |  |  |
| How to take length measurements | Blank= Not Completed |  |  |  |  |  |
| Length measurements should be taken from each circumference. It is recommended that you mark the leg with a non-permanent, non-toxic marker at each circumference measurement made. The length measurement is then taken even with the floor, along the inside of the leg, up to each circumference point. |  |  |  |  |  |
| Employee Demonstrated and Verbalized the following: |  |  |  |  |  |  |  |
| Measurement Points Knee High Stockings with Tape Measure |  |  |  |  |  |  |  |
| A. Measure Length from A to D bottom of foot to back of knee. |  |  |  |  |  |  |  |
| B. Circumference point Ankle is the area of greatest compression and therefore the most important point. This measurement is the smallest circumference of the ankle found closest to and above the ankle bone. |  |  |  |  |  |  |  |
| C. Circumference point Calf is the largest circumference of the calf. |  |  |  |  |  |  |  |
|  |  | Table B |
| Using Measurements to Size |  |  |
| Able to take Measurements from A-C and select appropriate Size from Chart |  |  |
| Documentation |  |  |
| Adds Comment to Stocking Consult in CPRS for Proper Size and Informs Veteran if on West Haven or Newington Campus to pick them up in Prosthetics or if in CBOCs they will be Mailed. |  |  |
| Employee Signature/Date |  |  |
| Evaluator Signature/Date |  |  |